## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 6 |  | Plan Duration | [5 empty] | % Complete |  |  | Actual (beyond plan) |  |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Team formation | 1 | 1 | 1 | 1 | 100%
Research on data availability | 1 | 2 | 1 | 3 | 100%
Research on development environment | 1 | 2 | 1 | 2 | 100%
Collect sample data | 2 | 2 | 2 | 1 | 100%
Setting up environment | 2 | 1 | 2 | 1 | 100%
Built an to-do list App as demo | 2 | 2 | 2 | 2 | 100%
Sample Data Normalization | 3 | 2 | 3 | 1 | 100%
Exploration on available UI design | 3 | 1 | 3 | 2 | 100%
Establish basic UI | 3 | 2 | 3 | 2 | 100%
Setting up platform for Map | 4 | 2 | 4 | 2 | 100%
Algorithms for simple data normalization | 4 | 3 | 5 | 2 | 100%
Search on Map | 4 | 1 | 4 | 1 | 100%
Zoom in & Zoom out | 4 | 1 | 4 | 1 | 100%
Switch between different layer | 4 | 1 | 5 | 1 | 100%
Large data collection | 5 | 2 | 5 | 2 | 100%
Data visualization on basic data (wind, solar, water) | 5 | 2 | 5 | 2 | 100%
First delieverable
Further algorithm deveplment for other data normalization | 7 | 1 |  |  | 0%
User select area function | 7 | 1 |  |  | 0%
Further data visualization on other data | 7 | 2 |  |  | 0%
User-frendly interface improvement | 8 | 2 |  |  | 0%
Apply calculation algorithm | 8 | 2 |  |  | 0%
Implementational cost from energy grid data | 8 | 2 |  |  | 0%
Combine result data and location | 8 | 2 |  |  | 0%
Visualize evaluation result | 8 | 2 |  |  | 0%
Implement functional energy calculation | 9 | 2 |  |  | 0%
Provide an energy evaluation services prototype | 9 | 2 |  |  | 0%
System integration Test | 9 | 2
User Acceptance Test | 10 | 1
Second delieverable (MVP)
Mechine learning on combination of technologies | TBD | TBD
More consideration on algorithm efficiency | TBD | TBD
Calculate implementation cost | TBD | TBD
Evaluate return of investment | TBD | TBD
Improvement on website design | TBD | TBD
Accpetance Test | TBD | TBD
Third delieverable

## Sheet1
Features | Description | Schedule Completion Week | Actual Completion Week
A Map base website | A map engine is included in a website. Allow user to simply move around the map
Basic button include "Home", "News", "Contact", "About" | Display general information
Allow user to search on the map base on their input | A search box on the map allow the user to input the map area they would like to see
Integrate above function on one website
Side bar available | Including some dummy button to have a feel of the user interface
Switch between differernt base map | Switch between solar/wind/water
Switch between differernt map data | Different map layer visualized for differernt energy. Example: wind at 10m, wind at 50m.