## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 2 |  | Plan Duration | [5 empty] | % Complete |  |  | Actual (beyond plan) |  |  |  | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Team formation | 1 | 1 | 1 | 1 | 100%
Research on data availability | 1 | 2 | 1 | 3 | 50%
Research on development environment | 1 | 2 | 1 | 2 | 100%
Collect sample data | 2 | 2 | 2 | 1 | 50%
Setting up environment | 2 | 1 | 2 | 1 | 100%
Built an to-do list App as demo | 2 | 2 | 2 | 2 | 100%
Sample Data Normalization | 3 | 2 | 3 | 1 | 25%
Exploration on available UI design | 3 | 1 |  |  | 0%
Algorithm Brainstroming | 3 | 1 |  |  | 0%
Setting up platform for Map | 4 | 2 |  |  | 0%
Create algorithms | 4 | 3 |  |  | 0%
Create other calculations for P/L | 4 | 3 |  |  | 0%
Set up database | 4 | 3 |  |  | 0%
Nomarlize large data set | 4 | 3 |  |  | 0%
Test sample data on algorithms | 5 | 2 |  |  | 0%
Test map functionality base on dummy data | 5 | 2 |  |  | 0%
First delieverable
Algorithm deveplment | 6 | 3 |  |  | 0%
Complete data collection | 6 | 6 |  |  | 0%
Establish basic UI | 6 | 1 |  |  | 0%
User-frendly interface improvement | 7 | 2 |  |  | 0%
Apply calculation algorithm | 7 | 1 |  |  | 0%
Workable Energy calculator | 7 | 1 |  |  | 0%
Combine result data and location | 8 | 1 |  |  | 0%
Visualize evaluation result | 8 | 1 |  |  | 0%
Implement functional website | 8 | 3 |  |  | 0%
Provide an energy evaluation services prototype | 8 | 4 |  |  | 0%
Second delieverable
Mechine learning