## Sheet1
ENERGY STORAGE RIGHTS
Week
| TASK DESCRIPTION | PLAN START (Inclusive) | PLAN END (Inclusive) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  |  | First Stage |  |  |  |  | Second Stage
Front-end (Web)
1 | 1st Technical Reivew -Review code readability, cohesion and coupling -Review program structure and architecture -Review compatibility | 2 | 3 | bar: Week 2 to Week 3
2 | User interface design research | 2 | 4 | bar: Week 2 to Week 4
3 | User interface development and improvement -Refine more User friendly UI plan -Self-review previous UI structure -Improve and develop on the information panel | 2 | 4 | bar: Week 2 to Week 4
4 | System integration testing on basic function on website (TC01-TC06) -Internal testing | 4 | 5 | bar: Week 4 to Week 5
5 | Develop onboarding information page Use short, clear, subtle images and video, and plenty of personality in its user onboarding flow to welcome new users and introduce important features. -User Manual/Guide -FAQ -Tooltip -Hint | 4 | 5 | bar: Week 4 to Week 5
6 | Improve UI design through User Acceptance Testing and feedback -User testing -Refine more User friendly UI -Improve base on the feedback and development | 5 | 7 | bar: Week 5 to Week 7
7 | Web host provider research and usage for backend -Explore common web server provider -Understand how web server works -Explore on the pros and cons of different solution -Compare compatibility, server performance, price, features, customer supports, and server physical locations. | 2 | 4 | bar: Week 2 to Week 4
8 | Initial host implementation and Development | 3 | 7 | bar: Week 3 to Week 7
9 | Create Test Case for host implementation and web server stability and reliability testing | 4 | 5 | bar: Week 4 to Week 5
10 | Review Web server integration and testing | 5 | 7 | bar: Week 5 to Week 8
11 | Web server stability and reliability testing | 6 | 9 | bar: Week 6 to Week 9
12 | 2nd Technical Reivew -Review code readability, cohesion and coupling -Review program structure and architecture -Review compatibility | 9 | 9 | bar: Week 9
13 | Preprae handover documentation | 9 | 9 | bar: Week 9
Back-end (Algorithm)
1 | Review Energy Algorithm Implemented -Prepare Algorithm Documentation and presentation -Prepare sample data and review testing result | 2 | 2 | bar: Week 2
2 | Explore large data storage option | 2 | 3 | bar: Week 2 to Week 3
3 | Research on other possible energy algorithm | 3 | 3 | bar: Week 3
4 | Research on Algorithm/Data for implementation cost within Australia | 3 | 4 | bar: Week 3 to Week 4
5 | Research on Algorithm/Data for implementation cost Globally | 3 | 4 | bar: Week 3 to Week 4
7 | Integrate algorithm with existing website | 5 | 6 | bar: Week 5 to Week 6
8 | Select sample data that could be used for ML model | 6 | 6 | bar: Week 6
9 | Train ML model using selected data | 6 | 8 | bar: Week 6 to Week 8
10 | Verify ML model accuracy on known location | 6 | 9 | bar: Week 6 to Week 9
11 | Integrate ML model with existing website | 8 | 10 | bar: Week 8 to Week 10