## Sheet1
Energy Storage Rights - Work Logs | [7 empty] | Total Working Hours: | 18.5
Date | Time | Duration |  | Yunyuan Yu | Yuanxin Ye | Weiwei Liang | Daoyu Li | Dawei Zhang | Peilin Song | Yufei Qian | Achievement | Remarks
2019-05-22 | 20:00 | 4 Hours | 4 | Change the code for energy calculation algorithm and code for popup display. Fix bugs that causing incorrect display of return of investment. Work together with Peilin. |  |  |  |  | Update HTML and CSS Style file according to the change required. Work together with Yunyuan. |  | Allow the update button to work with wind and solar. Fix the bugs where the change in number of electricity prices does not affect the final return of investment. Redesign UI to display extra information. | Change after audit 3 in semester 1
2019-08-01 | 14:00 | 3 Hours | 3 | Distribute tasks plan project schedule and priority base on the dependencies of each task. Document task for the first 2 weeks for each one. Work together with Peilin, Yuanxin | Modified statement of work. Readjut deliverable base on the client feedback. Work together with Peilin |  | Review and update risk register base on the feedback. | Research and explore different web cloud service including AWS, heroku, digital ocean. Work together with Daoyu | Draw Gantt Chart in excel to illustrate the project schedule. Work with Yunyuan |  | Update Statement of Work Update Risk Register Create a new Gantt Chart
2019-08-01 | 19:00 | 3 Hours | 3 |  |  | Work on Stakeholder matrix, stakeholder analysis and declare clearly key stakeholders and their expectations. Plan and document stakeholders communication tools and channels. |  | Explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. |  | Work on algorithm includes improving formula, test on different dataset and analyse results. Work together with Weiwei | Prepare to present algorithm for both technical and non-technical audience.
2019-08-04 | 15:00 | 1.5 Hours | 1.5 | Research on the possible todo under each task. Modified schedule to be more detailed and more specific base on research on similar project. Work together with Daoyu | Create presentation slides for reflection. | Create initial version of audit presentation slides. Work together with Daoyu. | Research on the possible todo under each task. Modified schedule to be more detailed and more specific base on research on similar project. Work together with Yunyuan |  |  | Create current algorithm presentation slides for client and store within Google Drive. Review documentation in algorithm folder. Work together with Weiwei | Update Statement of Work Update Gantt Chart Create slides for presentation
2019-08-04 | 16:30 | 15 Mins | 0.25 | Review the feedback from last audit in last semester.
2019-08-04 | 16:45 | 15 Mins | 0.25 | Review first version of presentation slide; Review schedule to make sure it is feasible.
2019-08-04 | 17:00 | 1 Hour | 1 | Fixing critical bug that causing the pop up box failure to display upon user click. Work together with Peilin | Continue refine statement of work.Review information on other section in SOW.Work together with Daoyu | Refine presentation slides base on the team's feedback. | Continue refine statement of work.Review information on other section in SOW. Work together with Yuanxin | Upload data into cloud. | Fixing critical bug that causing the pop up box failure to display upon user click. Work together with Yunyuan | Create current algorithm presentation slides for client and store within Google Drive. Review documentation in algorithm folder. Work together with Weiwei | Algorithm presentation slides is ready
2019-08-04 | 18:00 | 2 Hours | 2 | reorganize Github directory. Work with Yuanxin | Continue refine statement of work.Review information on other section in SOW.Work together with Daoyu | Refine presentation slides base on the team's feedback. Work together with Yufei | Continue refine statement of work.Review information on other section in SOW. Work together with Yuanxin |  |  | Refine presentation slides base on the team's feedback. Work together with Weiwei | Finished editing SOW and reorganize GitHub
2019-08-04 | 20:00 | 2 Hours | 2 |  |  |  |  | Furthur explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. Work together with Peilin | Furthur explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. Work together with Dawei
2019-08-06 | 15:30 | 1.5 Hour | 1.5 | Finalize Audit presentation, divide the work for Audit Presentation
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0