## Sheet1
Energy Storage Rights - Work Logs
Date | Time | Duration | Yunyuan Yu | Yuanxin Ye | Weiwei Liang | Daoyu Li | Dawei Zhang | Peilin Song | Yufei Qian | Achievement | Remarks
2019-05-22 | 20:00 | 4 Hours | Change the code for energy calculation algorithm and code for popup display. Fix bugs that causing incorrect display of return of investment. Work together with Peilin. |  |  |  |  | Update HTML and CSS Style file according to the change required. Work together with Yunyuan. |  | Allow the update button to work with wind and solar. Fix the bugs where the change in number of electricity prices does not affect the final return of investment. Redesign UI to display extra information. | Change after audit 3 in semester 1
2019-08-01 | 14:00 | 3 Hours | Distribute tasks plan project schedule and priority base on the dependencies of each task. Document task for the first 2 weeks for each one. Work together with Peilin, Yuanxin | Modified statement of work. Readjut deliverable base on the client feedback. Work together with Peilin |  | Review and update risk register base on the feedback. | Research and explore different web cloud service including AWS, heroku, digital ocean. Work together with Daoyu | Draw Gantt Chart in excel to illustrate the project schedule. Work with Yunyuan |  | Update Statement of Work Update Risk Register Create a new Gantt Chart