## Sheet1
ENERGY STORAGE RIGHTS
Week
| TASK DESCRIPTION | PLAN START (Inclusive) | PLAN END (Inclusive) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
|  |  |  | First Stage |  |  |  |  | Second Stage
Front-end (Web)
1 | UI research for better design on similar websites | 2 | 3 | bar: Week 2 to Week 3
2 | Refine more User friendly UI plan | 2 | 4 | bar: Week 2 to Week 4
3 | Self-review previous UI design | 4 | 4 | bar: Week 4
4 | User testing on prototype | 5 | 5 | bar: Week 5
5 | Improve UI design through user feedback | 5 | 6 | bar: Week 5 to Week 6
6 | Create onboarding information page | 6 | 6 | bar: Week 6
7 | 1st Review code cleaness and code efficiency | 2 | 3 | bar: Week 2 to Week 3
8 | 2nd Review code cleaness and code efficiency | 7 | 7 | bar: Week 7
9 | Web server research and usage for backend | 2 | 4 | bar: Week 2 to Week 4
10 | Initial Web server testing | 3 | 5 | bar: Week 3 to Week 5
11 | Web server comparison and selection | 5 | 5 | bar: Week 5
12 | Implement Web server integration | 5 | 8 | bar: Week 6 to Week 8
13 | Web server stability and reliability testing | 6 | 9 | bar: Week 6 to Week 9
Back-end (Algorithm)
1 | Review Energy Algorithm Implemented | 2 | 2 | bar: Week 2
2 | Explore large data storage option | 2 | 3 | bar: Week 2 to Week 3
3 | Research on other possible energy algorithm | 3 | 3 | bar: Week 3
4 | Research on algorithm for implementation cost within Australia | 3 | 4 | bar: Week 3 to Week 4
5 | Research on algorithm for implementation cost Globally | 3 | 4 | bar: Week 3 to Week 4
6 | Test with sample data | 4 | 5 | bar: Week 4 to Week 5
7 | Integrate algorithm with existing website | 5 | 6 | bar: Week 5 to Week 6
8 | Select sample data that could be used for ML model | 6 | 6 | bar: Week 6
9 | Train ML model using selected data | 6 | 8 | bar: Week 6 to Week 8
10 | Verify ML model accuracy on known location | 6 | 8 | bar: Week 6 to Week 8
11 | Integrate ML model with existing website | 8 | 10 | bar: Week 8 to Week 10