## Worksheet
Energy Storage Rights - Work Logs | [8 empty] | Total Working Hours: | 75.5
Date | Time | Duration |  |  | Yunyuan Yu | Yuanxin Ye | Weiwei Liang | Daoyu Li | Dawei Zhang | Peilin Song | Yufei Qian | Achievement | Remarks
|  | Total |  |  | 61.5 | 60.5 | 60.5 | 60.5 | 60.5 | 61 | 61.5
2019-05-22 | 20:00 | 4 Hours | 4 | 4 | Change the code for energy calculation algorithm and code for popup display. Fix bugs that causing incorrect display of return of investment. Work together with Peilin. |  |  |  |  | Update HTML and CSS Style file according to the change required. Work together with Yunyuan. |  | Allow the update button to work with wind and solar. Fix the bugs where the change in number of electricity prices does not affect the final return of investment. Redesign UI to display extra information. | Change after audit 3 in semester 1
2019-08-01 | 14:00 | 3 Hours | 3 | 7 | Distribute tasks plan project schedule and priority base on the dependencies of each task. Document task for the first 2 weeks for each one. Work together with Peilin, Yuanxin | Modified statement of work. Readjut deliverable base on the client feedback. Work together with Peilin | Work on Stakeholder matrix, stakeholder analysis and declare clearly key stakeholders and their expectations. Plan and document stakeholders communication tools and channels. | Review and update risk register base on the feedback. | Research and explore different web cloud service including AWS, heroku, digital ocean. Work together with Daoyu | Draw Gantt Chart in excel to illustrate the project schedule. Work with Yunyuan |  | Update Statement of Work Update Risk Register Create a new Gantt Chart
2019-08-01 | 19:00 | 3 Hours | 3 | 10 | Modified statement of work. Readjut deliverable base on the client feedback. | Modified statement of work. Readjut deliverable base on the client feedback. | Work on Stakeholder matrix, stakeholder analysis and declare clearly key stakeholders and their expectations. Plan and document stakeholders communication tools and channels. | Review and update risk register base on the feedback. | Explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. |  | Work on algorithm includes improving formula, test on different dataset and analyse results. Work together with Weiwei | Prepare to present algorithm for both technical and non-technical audience.
2019-08-04 | 15:00 | 1.5 Hours | 1.5 | 11.5 | Research on the possible todo under each task. Modified schedule to be more detailed and more specific base on research on similar project. Work together with Daoyu | Create presentation slides for reflection. | Create initial version of audit presentation slides. Work together with Daoyu. | Research on the possible todo under each task. Modified schedule to be more detailed and more specific base on research on similar project. Work together with Yunyuan | Explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. |  | Create current algorithm presentation slides for client and store within Google Drive. Review documentation in algorithm folder. Work together with Weiwei | Update Statement of Work Update Gantt Chart Create slides for presentation
2019-08-04 | 16:30 | 15 Mins | 0.25 | 11.75 | Review the feedback from last audit in last semester.
2019-08-04 | 16:45 | 15 Mins | 0.25 | 12 | Review first version of presentation slide; Review schedule to make sure it is feasible.
2019-08-04 | 17:00 | 1 Hour | 1 | 13 | Fixing critical bug that causing the pop up box failure to display upon user click. Work together with Peilin | Continue refine statement of work.Review information on other section in SOW.Work together with Daoyu | Refine presentation slides base on the team's feedback. | Continue refine statement of work.Review information on other section in SOW. Work together with Yuanxin | Upload data into cloud. | Fixing critical bug that causing the pop up box failure to display upon user click. Work together with Yunyuan | Create current algorithm presentation slides for client and store within Google Drive. Review documentation in algorithm folder. Work together with Weiwei | Algorithm presentation slides is ready
2019-08-04 | 18:00 | 2 Hours | 2 | 15 |  | Continue refine statement of work.Review information on other section in SOW.Work together with Daoyu | Refine presentation slides base on the team's feedback. Work together with Yufei | Continue refine statement of work.Review information on other section in SOW. |  |  | Refine presentation slides base on the team's feedback. Work together with Weiwei | Finished editing SOW and reorganize GitHub
2019-08-04 | 20:00 | 2 Hours | 2 | 17 |  |  |  |  | Furthur explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. Work together with Peilin | Furthur explore on the products commonly used for web server and briefly understand how it should be used, what factors will have high influence on the implementation. Work together with Dawei | Research on maintainence cost for solar
2019-08-06 | 15:30 | 1.5 Hour | 1.5 | 18.5 | Finalize Audit presentation, divide the work for Audit Presentation
2019-08-06 | 15:30 | 1.5 Hour | 1.5 | 20 | Meet with client, MEETING MINUTES 2
2019-08-14 | 15:30 | 1.5 Hour | 1.5 | 21.5 | Meet with client, MEETING MINUTES 3
2019-08-15 | 13:30 | 3 Hour | 3 | 24.5 | Remove GDAL, divide large data file into smaller data files | Update SOW with Weiwei | Update SOW with Yuanxin | Explore how to extract data from a WMS | Trying to implement webserver with Peilin | Trying to implement webserver with Dawei | Research on maintainence cost for solar
2019-08-15 | 17:00 | 1 Hour | 1 | 25.5 | Explore how to extract data from a WMS. Work together with Daoyu. | Update SOW with Weiwei | Update SOW with Yuanxin | Explore how to extract data from a WMS. Work together with Yunyuan. | Trying to implement webserver |  | Research on maintainence cost for solar
2019-08-15 | 20:00 | 2 Hour | 2 | 27.5 | [5 empty] | Set up bootstrap environment, Design a new navigation bar and side bar without functions. | Research on maintainence cost for wind
2019-08-21 | 16:00 | 2 Hour | 2 | 29.5 | Meet with client, MEETING MINUTES 4
2019-08-23 | 16:00 | 2 Hour | 2 | 31.5 | Meet with client, MEETING MINUTES 5
2019-08-25 | 13:00 | 6 Hour | 6 | 37.5 | Develop algorithm to compress data. Develop algorithm to divide data into smaller files. Distance to transmission line data from WMS is extracted, Continue to try to extract Pumped Hydro data. Work together with Daoyu | Update trelloe, Github | Research on cost for transmission line. Work together with Yufei | Distance to transmission line data from WMS is extracted, Continue to try to extract Pumped Hydro data. Work together with Yunyuan | Working with Heroku. Work together with Dawei. | Working with Heroku. Work together with Peilin. | Research on cost for transmission line. Work together with Weiwei
2019-08-27 | 15:00 | 3 Hour | 3 | 40.5 | Audit Presentation preparation | [6 empty] | Update risk.
2019-09-18 | 12:00 | 2 Hour | 2 | 42.5 | Tutorial, MEETING MINUTES 6
2019-09-27 | 16:00 | 3 Hour | 3 | 45.5 | Meeting with clients, MEETING MINUTES 7
2019-09-27 | 18:00 | 3 Hour | 3 | 48.5 | Try and test the data base and data storage platform one by one. Find out the best suitable one. | Extract and find out the possible decisions made throughout the meeting | Record and summarize the meeting details with client | Research on the possible downloadable online database and data storage platform | Use Google sheet to do the data storage | Try and test the Google API | Research and implement the algorithm on our platform.
2019-09-29 | 15:00 | 5 Hour | 5 | 53.5 | Try to integrate the current algorithm into our existing platform, i.e. Heroku | Do the agenda, decision log and reflection log | Work with Yuanxin to do the documentation | Work with Yunyuan to search for algorithm integration method | Work with Peilin and improve the UI interface | Upload and implement the current local website on Heroku | Contining researching and improving the algorithm on installation cost
2019-10-02 | 12:00 | 2 Hour | 2 | 55.5 | Tutorial
2019-10-03 | 15:00 | 7 Hour | 7 | 62.5 | Implement the pumped hydro | Design and implement the poster | Work with Yuanxin and draft the poster content | Work with Yunyuan to search for integration method | Improve the beauty of Interface | Use Photoshop to design and implement the poster | Contining researching and improving the algorithm on pumped hydro
2019-10-04 | 18:00 | 3 Hour | 3 | 65.5 |  | Finalize the poster | Finalize the poster | Finalize the poster | Finalize the poster | Finalize the poster | Finalize the poster
2019-10-06 | 17:00 | 5 Hour | 5 | 70.5 |  | Preparing the powerpoint for audit 3 | Preparing the powerpoint for audit 3 | SIT Testing | Integrate algorithm with website. Work together with Yufei, Peilin | Integrate algorithm with website. Work together with Yufei, Dawei | Integrate algorithm with website. Work together with Peilin, Dawei
2019-10-07 | 17:00 | 5 Hour | 5 | 75.5 | Implement the pumped hydro cost by current algorithm | Finalize Audit presentation, divide the work for Audit Presentation | Preparing the powerpoint for audit 3 | Working on implement local website to Heroku platform | Improve the Interface in terms of map and home page quality | Work with Dawei to improve our website interface | Work with Yunyuan and Daoyu to implement the algorithm
|  |  | 0 | 75.5
|  |  | 0 | 75.5
|  |  | 0 | 75.5

## Summary
Summary
Member | Yunyuan Yu | Yuanxin Ye | Weiwei Liang | Daoyu Li | Dawei Zhang | Peilin Song | Yufei Qian
Total Working hours | 61.5 | 60.5 | 60.5 | 60.5 | 60.5 | 61 | 61.5